## Tasks
Milestone 1: Project Setup
ID | Milestone | Task | Done When | Status | Assigned To
T-001 | Milestone 1: Project Setup | UI — VivViewer, image upload, h5ad upload, spot overlay, ROI drawing | VivViewer renders; spots overlay; ROI polygon drawable | Done
T-002 | Milestone 1: Project Setup | Infrastructure — routes.py, worker.py, inference.py, session.py | Chat endpoint streams tokens; session persists | Done
T-003 | Milestone 1: Project Setup | Preprocessing — QC, normalize, HVG, PCA (rag/preprocessing.py) | preprocess_adata() returns AnnData with X_pca | Done
T-004 | Milestone 1: Project Setup | Clustering — Leiden / KMeans, saves cluster JSON (rag/clustering.py) | run_spatial_clustering() saves cluster JSON with palette | Done
T-005 | Milestone 1: Project Setup | Mock RAG pipeline — sequential fallback (rag/pipeline.py) | _run_sequential() returns gene_objects, context_str, metadata | Done
T-006 | Milestone 1: Project Setup | Chat UI — AGENT TRACE card, pathway bar chart, DEG bar chart | All three panels render in chat after a query | Done
T-007 | Milestone 1: Project Setup | Folder structure — rag/deg/, rag/pathway/, rag/pubmed/, rag/agent/ | All subpackages importable with correct __init__.py exports | Done
Milestone 2: Preprocessing (rag/preprocessing.py)
ID | Milestone | Task | Done When | Status | Assigned To
T-033 | Milestone 2: Preprocessing (rag/preprocessing.py) | Add spot-level QC filtering — min genes per spot, max mitochondrial gene fraction | Spots below threshold removed before normalization; params are configurable | Open
T-034 | Milestone 2: Preprocessing (rag/preprocessing.py) | Store raw counts layer before normalization | adata.layers["counts"] present after preprocessing; DEG Wilcoxon reads from it | Open
T-035 | Milestone 2: Preprocessing (rag/preprocessing.py) | Cache preprocessed adata to disk | Re-running on same h5ad skips preprocessing and loads cache in < 1s | Open
T-036 | Milestone 2: Preprocessing (rag/preprocessing.py) | Write test_preprocessing.py | Tests: valid h5ad ok, missing spatial key raises ValueError, HVG reduces gene count, PCA present | Open
Milestone 3: Clustering (rag/clustering.py)
ID | Milestone | Task | Done When | Status | Assigned To
T-037 | Milestone 3: Clustering (rag/clustering.py) | Expose Leiden resolution as configurable parameter | run_spatial_clustering() accepts resolution kwarg; stored in cluster JSON | Open
T-038 | Milestone 3: Clustering (rag/clustering.py) | Add spatial coordinates as auxiliary features | Normalized x/y coordinates appended to PCA embedding before clustering | Open
T-039 | Milestone 3: Clustering (rag/clustering.py) | Support user-specified cluster count | run_spatial_clustering() accepts n_clusters override; skips auto-estimation | Open
T-040 | Milestone 3: Clustering (rag/clustering.py) | Cache cluster results | Skip re-clustering if cluster JSON exists and h5ad mtime unchanged | Open
T-041 | Milestone 3: Clustering (rag/clustering.py) | Write test_clustering.py | Tests: Leiden on small h5ad, KMeans fallback, palette has correct color count, JSON schema valid | Open
Milestone 4: DEG Extraction (rag/deg/)
ID | Milestone | Task | Done When | Status | Assigned To
T-008 | Milestone 4: DEG Extraction (rag/deg/) | Add Wilcoxon rank-sum test to _rank_high_expression_genes() | pvalue field present in each gene dict | Open
T-009 | Milestone 4: DEG Extraction (rag/deg/) | Add Benjamini-Hochberg correction | adj_pvalue field present; genes filtered to adj_pvalue < 0.05 | Open
T-010 | Milestone 4: DEG Extraction (rag/deg/) | Pre-filter candidates before Wilcoxon (performance) | Runs in < 10s for a 3000-spot dataset | Open
T-011 | Milestone 4: DEG Extraction (rag/deg/) | Write test_deg.py | Tests cover cluster selection, ROI selection, empty selection | Open
Milestone 5: Pathway Enrichment (rag/pathway/)
ID | Milestone | Task | Done When | Status | Assigned To
T-012 | Milestone 5: Pathway Enrichment (rag/pathway/) | Replace mock with real gseapy.enrichr() or g:Profiler API | Returns real GO/KEGG terms with valid adjusted p-values | Open
T-013 | Milestone 5: Pathway Enrichment (rag/pathway/) | Handle empty gene list and API errors | Returns [] without raising an exception | Open
T-014 | Milestone 5: Pathway Enrichment (rag/pathway/) | Write test_pathway.py | Tests cover happy path, empty input, API unavailability | Open
Milestone 6: PubMed Retrieval (rag/pubmed/)
ID | Milestone | Task | Done When | Status | Assigned To
T-015 | Milestone 6: PubMed Retrieval (rag/pubmed/) | Implement NCBI esearch + efetch calls | Returns real abstracts for a gene list | Open
T-016 | Milestone 6: PubMed Retrieval (rag/pubmed/) | Build query string from genes and pathways | Query combines gene symbols and pathway names | Open
T-017 | Milestone 6: PubMed Retrieval (rag/pubmed/) | Handle rate limiting and empty results | Returns [] without error; respects API rate limits | Open
T-018 | Milestone 6: PubMed Retrieval (rag/pubmed/) | Add vector store for semantic search (chromadb or faiss) | Fetched abstracts are embedded and searchable | Open
T-019 | Milestone 6: PubMed Retrieval (rag/pubmed/) | Write test_pubmed.py | Tests cover happy path, empty result, API unavailability | Open
Milestone 7: LangGraph Agent (rag/agent/)
ID | Milestone | Task | Done When | Status | Assigned To
T-020 | Milestone 7: LangGraph Agent (rag/agent/) | Define LangChain tools in tools.py: pathway_tool and pubmed_tool | Agent can call both tools (DEG runs automatically before the agent) | Open
T-021 | Milestone 7: LangGraph Agent (rag/agent/) | Implement real LangGraph agent in graph.py | Agent dynamically decides which tools to call based on the message | Open
T-022 | Milestone 7: LangGraph Agent (rag/agent/) | Dynamic trace field | metadata.trace reflects what the agent actually called, not a fixed list | Open
T-023 | Milestone 7: LangGraph Agent (rag/agent/) | Add max-iteration guard | Agent stops after 5 tool calls | Open
T-024 | Milestone 7: LangGraph Agent (rag/agent/) | Write test_agent.py | Agent calls at least one tool and returns complete output dict | Open
Milestone 8: Prompt Engineering (rag/agent/prompt.py)
ID | Milestone | Task | Done When | Status | Assigned To
T-025 | Milestone 8: Prompt Engineering (rag/agent/prompt.py) | Improve build_prompt_context() with domain framing | LLM identifies cell type, pathway activity, and clinical relevance | Open
T-026 | Milestone 8: Prompt Engineering (rag/agent/prompt.py) | Add structured citation instructions | LLM cites papers inline as [1], [2] consistently | Open
T-027 | Milestone 8: Prompt Engineering (rag/agent/prompt.py) | Test prompts against demo dataset | Responses are biologically relevant for the demo data | Open
Milestone 9: Demo Data & Evaluation
ID | Milestone | Task | Done When | Status | Assigned To
T-028 | Milestone 9: Demo Data & Evaluation | Download and validate spatial omics demo dataset | h5ad loads, spots overlay correctly, clustering runs | Open
T-029 | Milestone 9: Demo Data & Evaluation | End-to-end test with real data | Draw ROI → DEG → pathway → PubMed → streamed answer with citations | Open
T-030 | Milestone 9: Demo Data & Evaluation | Evaluate biological relevance of outputs | Genes and pathways make sense for the tissue type | Open
T-031 | Milestone 9: Demo Data & Evaluation | Record demo video | Shows ROI selection, AGENT TRACE, tool calls, streamed response | Open
T-032 | Milestone 9: Demo Data & Evaluation | Freeze final submission | Repo, docs, and demo complete | Open